## Work Instructions (hidden)
Work Instructions
General instructions: (Applies for all sheets)
- by default all sheets are protected to make clear what cells are editable and what cells do not require any input - please familiarise yourself with the workbook - you have to unprotect sheets to insert or delete rows within dynamic tables, e.g. Project List in 1 Controls - check the comments for help - to hide or show all comment go to the 'Review' ribbon and select 'Show All Comments' - comments will not be printed so hiding them is sufficient, you do not have to delete them - never delete activities that are rescheduled, but always set status to 'Rescheduled' and copy activity to desired week or date. This is important because the status report is automatically generated from the 3 Work Plan sheet and will not display rescheduled activities if they are removed from the respective week. The Status Report can not be edited or modified in any way. - exactly one deliverable, activity, project, etc. per row - only edit cells that have a yellow fill - don't edit cells that contain formulas - always ensure tables don’t contain empty rows - if locked cells with formulas do not contain the information you are expecting double-check the respective source-cells if the entered data is correct. Otherwise please contact email address below.
How To's
Protected Sheets | To see if a sheet is protected look for a little lock symbol next to the sheet name. If a sheet is locked only pre-defined cells can be selected and edited. Also no table rows or columns can be added or removed.
Protect / Unprotect Sheets | To protect or unprotect a sheet click the 'Unprotect Sheet' (if protected) or 'Protect Sheet' (if unprotected) button under the 'Review' ribbon.
Dynamic Tables | Dynamic tables can be recognised by a little blue corner or arrow symbol in the column. To add or remove rows in any dynamic table the respective sheet has to be unprotected. There are no tables in this workbook that require adding or removing rows that are not dynamic tables.
Editable Cells | All cells that are highlighted with a grey-yellow need to be edited.
Add Rows | To add a row to a dynamic table, please select the entire row below the dynamic table and press "'Shift' + 'Command' + '+'". Then just start typing in the new row below the dynamic table and it will automatically expand once you leave the cell.
To report issues, feedback or address questions, please contact: florian.kalbe@busanalysts.com.au

## 1 Controls
Controls Sheet | [6 empty] | 0%
[5 empty] | Completed | Unfinished | 5%
|  |  |  | Progress | 121 | -47 | 10%
|  |  |  | Activities | 60 | 64
Last Updated: |  |  |  | Deliverables | 4 | 0 | 15%
2020-10-30
20%
Client Name |  | Engagement Location | Effort in days |  |  |  | 25%
Higher Education / University |  | QLD | 40
SDM Name |  | Engagement Start |  | Sunday before Start
Jeremy Spencer |  | 2020-05-18 |  | 2020-05-17
Project Timeline |  | Initial Engagement End | Actual Engagement End
Fixed end date |  | 2020-08-27
Project Name | Status Group | Stage Start Date | Target Stage End Date
Student Experience - Credit Management | 1 | 2020-05-18 | 2020-08-27
Consultant Name | Consultant Initials | Consultant Role
BAPL Consultant | BC | Senior Business Analyst
Key Statistics
|  | Total number of weeks | 13
|  | Total number of working days | 74
|  | Total number of activities | 124
|  | Total number of deliverables | 4
|  | # Public holidays during engagement | 1
|  | Effort Balance | 0
Engagement Effort Variation
Reason | Type | Date | Amount in days
Leave
Formulas:
Sunday before Start = IF(WEEKDAY([Engagement Location],2)=7,[Engagement Location],[Engagement Location]-WEEKDAY([Engagement Location],2))
Note on A8: CLIENT NAME There is only one work plan per client so put the respective client name here and list all projects in the list starting in row 18.
Note on C8: LOCATION Please select the state in which the engagement takes place. This information is important because the public holidays for that specific state will be used in all fields containing dates throughout the work plan.
Note on D8: TOTAL ENGAGEMENT EFFORT The engagement end date will be calculated based on the total effort in days and the engagement start date.
Note on A9: EDITABLE CELLS Please only edit cells with this yellow fill.
Note on A14: PROJECT TIMELINE Fixed end date: The engagement end date can not be pushed back under any circumstances such as TOIL or leave. Flexible end date: The engagement end date can be pushed back if TOIL, leave or other factors lead to less consumption of effort than initially expected.
Note on C14: INITIAL END DATE This is the calculated end date in an ideal case without any interruptions, changes or additional leave, etc. The date is calculated based on networking days excluding weekends and public holidays (both for the state and national).
Note on D14: ACTUAL END DATE This is the actual end date which is calculated taking into account all changes in effort or duration entered in the bottom of this sheet in table 'Engagement Effort Variation'.
Note on B17: STATUS GROUP This field lets you group your projects for the status report. You can make up own groups containing different projects that you would like to create automated status reports for. That means if your client requests 1 status report for projects 1,2 and 3 then enter create one row for each project and put for example group name 'Project Group 1' into the 'Status Group' field of each project. Otherwise, put project stage.
Note on D18: RECOGNISING A TABLE The little blue corner on the bottom left indicates the last cell in a dynamic table. Please make sure there are not empty rows in any table at any time.
Note on A21: CONSULTANTS To add more consultants please refer to work instructions 'Add Rows' on how to add them to this this dynamic table.
Note on C24: STATS SUMMARY Automatically summarises data from other sheets. No action required.
Note on A41: EFFORT VARIATION REASON Please just write in free text what the cause for the reduction or increase of effort / duration was. E.g. 'Consultant X Sick Leave'
Note on D41: EFFORT VARIATION AMOUNT This field will be used as an input for the overall engagement timeline. Please put the amount of effort for each occasion in days. If effort will cause the engagement to end later, i.e. added on to the initial date then just put the number e.g. '6'. If effort will cause the engagement to end sooner than planned, i.e. reduce the initial date then just put the negative number by putting a 'minus' in front of it, e.g. '-3'.

## 2 Deliverables
Work Plan - Deliverables
Last Updated: | Client Name |  |  | Consultant Name
2020-10-30 | Higher Education / University |  |  | NP
| Due Dates |  |  | Status
Deliverable | Internal Peer Review Date | Client Review Date | Due Delivery Date | Hard Constraint / Estimated | Project | % Done | Consultant Responsible | Notes
Service Delivery Specification (SDS) | 2020-05-19 | Not required | 2020-05-20 | Estimated | Student Experience - Credit Management | 100% | NP | Updated 18/05 and sent to Sponsor for approval. Sponsor has approved this.
Engagement Workplan | 2020-05-19 | 2020-05-20 | 2020-05-20 | Estimated | Student Experience - Credit Management | 100% | NP | Shared with Sponsor and Project Manager.
Workshop Approach | Not required | 2020-07-15 | 2020-07-17 | Estimated | Student Experience - Credit Management | 100% | NP
Customer Journey Maps and Personas | 2020-07-13 | 2020-07-15 | 2020-07-17 | Estimated | Student Experience - Credit Management | 100% | NP
Note on A6: DATE Always updates automatically to the last day opened.
Note on E6: SHEET HEADER Please select lead BA for the project. Has to match the following sheets.
Note on A9: DELIVERABLES Please only insert deliverables here that are listed in the SDS. All intermediate milestones and components will be listed in '3 Work Plan'.
Note on B9: DEADLINES If not applicable, please enter same date as in Due Delivery Date. Otherwise, graph in 6 Engagement Timeline will be inaccurate.
Note on E9: CONSTRAINT If the due delivery date is a hard constraint, choose 'Hard constraint'. This means it cannot be moved due to client requirements or regulatory requirements, etc. If the due delivery date is arbitrary and based on estimations / planning only, put 'Estimated'.
Note on F9: PROJECTS If your project is not shown, add respective project to Project List in '1 Controls'.

## 3 Work Plan
Work Plan - Activities
Last Updated: |  |  | Client Name | Consultant Name
2020-10-30 |  |  | Higher Education / University | NP
Week | Dates | Day | Activities | Status | Project | Initials | Dependencies | Comments | Deliverable (optional) | Is Holiday | Status Group
-28 | 2019-11-04 | 2019-11-04 | Introduction to engagement and key stakeholders | Completed | Core Banking Transformation | RDW | None | Met with Richard Claydon and Ashley X. Later in the morning with Darren X. |  | FALSE | #N/A
-28 | 2019-11-04 | 2019-11-04 | Induction reading | Completed | Core Banking Transformation | RDW | None | Please see email to Richard confirming. |  | FALSE | #N/A
-28 | 2019-11-04 | 2019-11-04 | Transformation introduction session (101) | Completed | Core Banking Transformation | RDW | None | Where it's at now. Transformation group explanation and sponsors for each group. |  | FALSE | #N/A
-28 | 2019-11-04 | 2019-11-04 | Transformation for the Platforms and Technology - Core Banking group specifically | Completed | Core Banking Transformation | RDW | None | Identification of the way to proceed with the process/transactions using the usage report. |  | FALSE | #N/A
-28 | 2019-11-08 | 2019-11-08 | Develop work plan according to information collected and agreed for this engagement | Completed | Core Banking Transformation | RDW | None | According to day one interactions. |  | FALSE | #N/A
-28 | 2019-11-05 | 2019-11-05 | Ashley catch-up | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-05 | 2019-11-05 | Develop collection spreadsheet | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-05 | 2019-11-05 | Initial meeting with Contact Centre | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-05 | 2019-11-05 | Agreed question to be asked during active observations | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-06 | 2019-11-06 | Active observation day session one - Contact Centre, General | Completed | Core Banking Transformation | RDW | None | Processes dictated by call content - Groups 4.0 and 5.0 expected. |  | FALSE | #N/A
-28 | 2019-11-06 | 2019-11-06 | Capture call content including users method of accessing core and what is run for each call. | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-06 | 2019-11-06 | Weekly Transformation meeting | Completed | Miscellaneous time | RDW | None | Weekly meeting for status check. |  | FALSE | #N/A
-28 | 2019-11-07 | 2019-11-07 | Transfer Contact Centre use case notes to template - Session 1 | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-07 | 2019-11-07 | Update collection template with feedback | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-07 | 2019-11-07 | Walkthrough and agree changes with Richard | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-08 | 2019-11-08 | Agree stakeholder sessions with Richard | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-28 | 2019-11-08 | 2019-11-08 | Book sessions for Week 2 | Completed | Core Banking Transformation | RDW | None | Booking is being done one week out at this stage. |  | FALSE | #N/A
-28 | 2019-11-08 | 2019-11-08 | Active observation half day session two - Contact Centre, Retention and Email Queries | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-27 | 2019-11-11 | 2019-11-11 | Transfer Contact Centre use case notes to template - Session 2 | Completed | Core Banking Transformation | RDW | None | Second session. |  | FALSE | #N/A
-27 | 2019-11-11 | 2019-11-11 | Active observation day session one - Operations | Completed | Core Banking Transformation | RDW | None | Susan |  | FALSE | #N/A
-27 | 2019-11-12 | 2019-11-12 | Active observation day session two - Operations | Completed | Core Banking Transformation | RDW | None |  |  | FALSE | #N/A
-27 | 2019-11-13 | 2019-11-13 | Active observation HALF day session three - Operations | Completed | Core Banking Transformation | RDW | None | Conducted after lunch due to Roadshow. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-27 | 2019-11-13 | 2019-11-13 | Transfer Operations use case notes to template - Day 1/2. | Completed | Core Banking Transformation | RDW | None | Data entry and updates during Roadshow. |  | FALSE | #N/A
-27 | 2019-11-14 | 2019-11-14 | Active observation day session four - Operations | Completed | Core Banking Transformation | RDW | None | Started this one early to capture processing. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-27 | 2019-11-15 | 2019-11-15 | Transfer Operations use case notes to template - week 2 | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-22 | 2019-11-22 | Tentative for Petrie visit to Brokers | Completed | Core Banking Transformation | RDW | None | Prebook parking as Earlybird The Barracks Carpark | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-27 | 2019-11-15 | 2019-11-15 | Active observation day session three - Contact Centre, Sales | Rescheduled | Core Banking Transformation | RDW | None | This is ongoing through the week in the afternoons. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-27 | 2019-11-15 | 2019-11-15 | Active observation session Payroll - Operations | Rescheduled | Core Banking Transformation | RDW | None | No transactions on Monday so need to go back. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-18 | 2019-11-18 | Active observation session - Credit Operations | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-19 | 2019-11-19 | Active observation session - Credit Operations Collections and Remediations | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-19 | 2019-11-19 | Active observation session Payroll - Operations | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-20 | 2019-11-20 | Active observation day session catch up - Contact Centre, Sales | Rescheduled | Core Banking Transformation | RDW | None | Tentative catch up session. Expectation is Credit Operations will complete earlier than scheduled. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-21 | 2019-11-21 | Transfer Operations use case notes to template | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-25 | 2019-11-25 | Active observations session - Broker Support & Retail Reporting | Rescheduled | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-26 | 2019-11-26 | Active observation session 1 - Branch | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-27 | 2019-11-27 | Active observation session 2 - Branch | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-28 | 2019-11-28 | Active observation session 3 - Branch | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-29 | 2019-11-29 | Collation day - half day | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-24 | 2019-12-02 | 2019-12-02 | Active observation day session catch up - Contact Centre, Sales - morning | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-26 | 2019-11-20 | 2019-11-20 | Collation day | Completed | Core Banking Transformation | RDW | None | Due to Credit Operations not being available. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-24 | 2019-12-02 | 2019-12-02 | Active observations session - Broker Support & Retail Reporting - afternoon | Completed | Core Banking Transformation | RDW | None | Due to illness | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-25 | 2019-11-25 | Part day transfer of use case notes to template | Completed | Core Banking Transformation | RDW | None | Due to illness | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-26 | 2019-11-26 | Part day transfer of use case notes to template | Completed | Core Banking Transformation | RDW | None | Due to half days in branch, no new transactions so chose to populate collection template instead. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-28 | 2019-11-28 | Part day transfer of use case notes to template | Completed | Core Banking Transformation | RDW | None | Due to half days in branch, no new transactions so chose to populate collection template instead. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-28 | 2019-11-28 | Future - planning session with RC | Completed | Miscellaneous time | RDW | None | Planning for last quarter of initial and post initial engagement. | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
-25 | 2019-11-29 | 2019-11-29 | Active observation Financial Crimes team - afternoon | Completed | Core Banking Transformation | RDW | None |  | Core Banking Use Case Analysis Catalogue | FALSE | #N/A
1 | 2020-05-18 | 2020-05-18 | Kick-off, Access to Docuemntation and Systems, Discussion of the stakeholders and plan for workshops | Completed | Student Experience - Credit Management | BC | None | Access to Teams | Not Applicable | FALSE | 1
1 | 2020-05-18 | 2020-05-18 | Update the SDS | Completed | Student Experience - Credit Management | BC | None | Updated and sent to Sponsor for sign-off | Service Delivery Specification (SDS) | FALSE | 1
1 | 2020-05-19 | 2020-05-19 | Communicate Workshop Approach for discussion with Sponsor and Project Manager | Completed | Student Experience - Credit Management | BC |  |  | Not Applicable | FALSE | 1
1 | 2020-05-19 | 2020-05-19 | Create Workplan | Completed | Student Experience - Credit Management | BC |  |  | Engagement Workplan | FALSE | 1
1 | 2020-05-19 | 2020-05-19 | Distribute Workplan to Sponsor and Project Manager | Completed | Student Experience - Credit Management | BC |  |  | Not Applicable | FALSE | 1
1 | 2020-05-19 | 2020-05-19 | Distribute Workshop Approach to Sponsor and Project Manager | Completed | Student Experience - Credit Management | BC | None |  | Not Applicable | FALSE | 1
1 | 2020-05-20 | 2020-05-20 | Walkthrough of workshop approach with Sponsor and Project Manager | Completed | Student Experience - Credit Management | BC |  |  | Workshop Appraoch | FALSE | 1
1 | 2020-05-21 | 2020-05-21 | Credit Transfer Overview Brief with key stakeholders | Completed | Student Experience - Credit Management | BC | Availability of Stakeholders |  | Not Applicable | FALSE | 1
1 | 2020-05-22 | 2020-05-22 | Prepare Cust Journey Frameworks for the workshops next week | Completed | Student Experience - Credit Management | BC |  |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-25 | 2020-05-25 | Workshop 1: VET | Completed | Student Experience - Credit Management | BC | Availability of HE Stakeholders |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-25 | 2020-05-25 | Document outcomes from Workshop 1: Customer journey and Personas | Completed | Student Experience - Credit Management | BC | Workshop 1 |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-26 | 2020-05-26 | Document outcomes from Workshop 1: Customer journey and Personas | Completed | Student Experience - Credit Management | BC | Workshop 1 |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-27 | 2020-05-27 | Workshop 2: International | Completed | Student Experience - Credit Management | BC | Availability of International Stakeholders |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-27 | 2020-05-27 | Document outcomes from Workshop 2: Customer journey and Personas | Completed | Student Experience - Credit Management | BC | Workshop 2 |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-28 | 2020-05-28 | Workshop 3: HE | Completed | Student Experience - Credit Management | BC |  |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-28 | 2020-05-28 | Document outcomes from Workshop 3: Customer journey and Personas | Completed | Student Experience - Credit Management | BC | Workshop 2 |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-29 | 2020-05-29 | Document outcomes from Workshop 3: Customer journey and Personas | Completed | Student Experience - Credit Management | BC | Workshop 3 |  | Customer Journey Maps and Personas | FALSE | 1
2 | 2020-05-29 | 2020-05-29 | Document outcomes from Workshop 4: Customer journey and Personas | Completed | Student Experience - Credit Management | BC | Workshop 4 |  | Customer Journey Maps and Personas | FALSE | 1
3 | 2020-06-01 | 2020-06-01 | Document the High Level Human Centred Design Themes and Principles. | In Progress | Student Experience - Credit Management | BC | Workshop 3 |  | High Level Customer Journey Future Visioning | FALSE | 1
3 | 2020-06-01 | 2020-06-01 | As-Is Mini planning sessin (Domestic HE to HE, Project Manager) | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
3 | 2020-06-01 | 2020-06-01 | High Level Human Centred Design Themes and Principles. | In Progress | Student Experience - Credit Management | BC |  |  | High Level Customer Journey Future Visioning | FALSE | 1
3 | 2020-06-02 | 2020-06-02 | Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
3 | 2020-06-03 | 2020-06-03 | Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
3 | 2020-06-04 | 2020-06-04 | Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
3 | 2020-06-05 | 2020-06-05 | Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
4 | 2020-06-08 | 2020-06-08 | Workshop 6: VET follow up workshop | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
4 | 2020-06-08 | 2020-06-08 | Document outcomes from Workshop 6: Customer journey and As-Is Business Process updates | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
4 | 2020-06-09 | 2020-06-09 | Workshop 5: International follow up | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
4 | 2020-06-10 | 2020-06-10 | Workshop 4: HE - Follow up | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
4 | 2020-06-10 | 2020-06-10 | Document outcomes from Workshop 4: Customer journey and As-Is Business Process updates | Not Started | Student Experience - Credit Management | BC | Workshop 4 |  | Customer Journey Maps | FALSE | 1
4 | 2020-06-11 | 2020-06-11 | Document outcomes from Workshop 4: Customer journey and As-Is Business Process updates | Not Started | Student Experience - Credit Management | BC | Workshop 4 |  | Customer Journey Maps | FALSE | 1
4 | 2020-06-12 | 2020-06-12 | Document outocmes from follow-up workshops | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
5 | 2020-06-15 | 2020-06-15 | FEEDBACK POINT: Distribute CJMs and Business Processes for Review | Not Started | Student Experience - Credit Management | BC |  |  | Business Process Maps (Level 3) | FALSE | 1
5 | 2020-06-16 | 2020-06-16 | Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
5 | 2020-06-17 | 2020-06-17 | Targeted feedback, 1-on-1 sessions and updates of CJMs and To-Be Business Processes | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
5 | 2020-06-18 | 2020-06-18 | Targeted feedback, 1-on-1 sessions and updates of CJMs and To-Be business processes | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
5 | 2020-06-19 | 2020-06-19 | Targeted feedback, 1-on-1 sessions and updates of CJMs and To-Be business processes | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
6 | 2020-06-22 | 2020-06-22 | Targeted feedback, 1-on-1 sessions and updates of CJMs and To-Be business processes | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
6 | 2020-06-23 | 2020-06-23 | Targeted feedback, 1-on-1 sessions and updates of CJMs and To-Be business processes | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
6 | 2020-06-23 | 2020-06-23 | FEEDBACK POINT: Distribute CJMs and Business Processes for Review | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
6 | 2020-06-24 | 2020-06-24 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
6 | 2020-06-25 | 2020-06-25 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
6 | 2020-06-26 | 2020-06-26 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
7 | 2020-06-29 | 2020-06-29 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
7 | 2020-06-30 | 2020-06-30 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
7 | 2020-07-01 | 2020-07-01 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
7 | 2020-07-02 | 2020-07-02 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
7 | 2020-07-03 | 2020-07-03 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
8 | 2020-07-06 | 2020-07-06 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
8 | 2020-07-07 | 2020-07-07 | Pre-Booked Leave | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
8 | 2020-07-08 | 2020-07-08 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
8 | 2020-07-09 | 2020-07-09 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
8 | 2020-07-10 | 2020-07-10 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
9 | 2020-07-13 | 2020-07-13 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
9 | 2020-07-14 | 2020-07-14 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
9 | 2020-07-14 | 2020-07-14 | FEEDBACK POINT: Distribute Gap Analysis and Improvements Findings | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
9 | 2020-07-15 | 2020-07-15 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
9 | 2020-07-16 | 2020-07-16 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
9 | 2020-07-17 | 2020-07-17 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
10 | 2020-07-20 | 2020-07-20 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
10 | 2020-07-21 | 2020-07-21 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
10 | 2020-07-22 | 2020-07-22 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
10 | 2020-07-23 | 2020-07-23 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
10 | 2020-07-24 | 2020-07-24 | Document Gap Analysis and identify improvements | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
11 | 2020-07-27 | 2020-07-27 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
11 | 2020-07-28 | 2020-07-28 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
11 | 2020-07-28 | 2020-07-28 | FEEDBACK POINT: Distribute Gap Analysis and Improvements Findings and the Recommendations Presentation. | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
11 | 2020-07-29 | 2020-07-29 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
11 | 2020-07-30 | 2020-07-30 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
11 | 2020-07-31 | 2020-07-31 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
12 | 2020-08-03 | 2020-08-03 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
12 | 2020-08-04 | 2020-08-04 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
12 | 2020-08-05 | 2020-08-05 | Outline recommendations presentation | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
12 | 2020-08-06 | 2020-08-06 | Present Recommendations to key stakeholders | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
12 | 2020-08-07 | 2020-08-07 | Contingency | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
13 | 2020-08-10 | 2020-08-10 | Contingency | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
13 | 2020-08-11 | 2020-08-11 | Contingency | Not Started | Student Experience - Credit Management | BC |  |  |  | FALSE | 1
13 | 2020-08-12 | Holiday | Engagement Close-Out | Not Started | Student Experience - Credit Management | BC | Close-Out |  |  | TRUE | 1
Formulas:
Day = IF(T_Activities[[#This Row],[Is Holiday]]=TRUE,"Holiday",T_Activities[[#This Row],[Dates]])
Note on B8: DATES You can have multiple rows with the same date
Note on C8: WEEK & DAY Never manually edit a 'Week' or 'Day' cell. They are automatically calculated based on the date. Depending on the State selected in 1 Controls, it displays the day of the week or displays 'Holiday' if it is a holiday in that state.
Note on D8: ACTIVITIES Please always have exactly one row for exactly one activity.
Note on E8: RESCHEDULED ACTIVITIES If you have to move an activity to another date or week, always leave the activity in the week you initially planned it and set the status to 'Rescheduled'. Then copy the same activity to the desired date.
Note on G8: CONSULTANT INITIALS Please select consultant initials for each activity.

## 4 Issues & Risks
Work Plan - Issues and Risks
|  | Last Updated: |  | Client Name |  | Consultant Name
|  | 2020-10-30 |  | Higher Education / University |  | NP
Issues
Status Group | Period | Date Raised | Name | Description | Potential Impact | Potential Solution | Project | Status
1 | 2 | 2020-05-25 | Nikesh Parbhoo | It takes too long to set the meeting stakeholders up correctly and thereafter be efficient in the workshop. Stakeholders have not been trained enough for this to be viable option where they contribute themselves to the Miro board | Not achieving the workshop outcomes in the allocated time. | Let only the main workshop team control the board. The stakeholders can have access to view how their contributions are being recorded (through sharing the Miro board through Zoom) | Student Experience - Credit Management | Resolved
#N/A | -6282
Risks
Status Group | Period | Date Raised | Name | Description | Potential Impact | Potential Mitigation | Project | Status
1 | 1 | 2020-05-22 | Nikesh Parbhoo | The relatively new way of working with Miro will likely present challenges to running the workshop efficiently | Medium | Train them through an intitial 15 minute crash course on Miro at the beginning of the session. Ensure that everybody is setup beforehand - this will be facilitated by Project Manager. | Student Experience - Credit Management | Resolved
1 | 2 | 2020-05-29 | Nikesh Parbhoo | Current focus is mainly on the Blue Sky thinking angle of the project. Week starting 1 June 2020 BAPL will be focusing on the As-Is business processes so that an anchor for the gap analysis is established. | Medium | BAPL has already started analysis work on the As-Is business processes. BAPL has also scheduled a process workshop kick-off with Domestic HE to HE for Monday 1 June 2020 | Student Experience - Credit Management | Open
#N/A | -6282
#N/A | -6282
#N/A | -6282
Note on I11: ISSUE & RISK REGISTER This is the register for all issues and risks for the entire engagement. Please do not delete any issues or risks once entered. Instead set the status to 'Resolved'

## 5 Status Report, Single Project
Status Report
Client Name |  | Consultant Name
Higher Education / University |  | Nikesh Parbhoo
Project Name | Start Date | End date
Student Experience - Credit Management | 2020-05-18 | 2020-08-27
|  |  | First Row of Current Period WP | First Row Next Period WP
Period Ending Date: | 2020-05-29 |  | 56 | 65
Week: | 2
Engagement Status: | Green |  | First Row of Current Period Issues | First Row Current Period Risks
Initiative is on track in terms of time, cost and quality of analysis work. No identified issues or risks are likely to impact initiative health. |  |  | 1 | 2
Current Week
Activity | Status | Completion Date | Nr | Period | Project
Workshop 1: VET | Completed | 2020-05-25 | 0 | 2 | Student Experience - Credit Management
Document outcomes from Workshop 1: Customer journey and Personas | Completed | 2020-05-25 | 1 | 2 | Student Experience - Credit Management
Document outcomes from Workshop 1: Customer journey and Personas | Completed | 2020-05-26 | 2 | 2 | Student Experience - Credit Management
Workshop 2: International | Completed | 2020-05-27 | 3 | 2 | Student Experience - Credit Management
Document outcomes from Workshop 2: Customer journey and Personas | Completed | 2020-05-27 | 4 | 2 | Student Experience - Credit Management
Workshop 3: HE | Completed | 2020-05-28 | 5 | 2 | Student Experience - Credit Management
Document outcomes from Workshop 3: Customer journey and Personas | Completed | 2020-05-28 | 6 | 2 | Student Experience - Credit Management
Document outcomes from Workshop 3: Customer journey and Personas | Completed | 2020-05-29 | 7 | 2 | Student Experience - Credit Management
Document outcomes from Workshop 4: Customer journey and Personas | Completed | 2020-05-29 | 8 | 2 | Student Experience - Credit Management
- | - | - | 9 | 3 | -
- | - | - | 10 | 3 | -
- | - | - | 11 | 3 | -
- | - | - | 12 | 3 | -
- | - | - | 13 | 3 | -
- | - | - | 14 | 3 | -
- | - | - | 15 | 3 | -
- | - | - | 16 | 4 | -
- | - | - | 17 | 4 | -
- | - | - | 18 | 4 | -
- | - | - | 19 | 4 | -
- | - | - | 20 | 4 | -
- | - | - | 21 | 4 | -
- | - | - | 22 | 4 | -
- | - | - | 23 | 5 | -
- | - | - | 24 | 5 | -
- | - | - | 25 | 5 | -
- | - | - | 26 | 5 | -
- | - | - | 27 | 5 | -
- | - | - | 28 | 6 | -
- | - | - | 29 | 6 | -
- | - | - | 30 | 6 | -
- | - | - | 31 | 6 | -
- | - | - | 32 | 6 | -
- | - | - | 33 | 6 | -
- | - | - | 34 | 7 | -
- | - | - | 35 | 7 | -
- | - | - | 36 | 7 | -
- | - | - | 37 | 7 | -
- | - | - | 38 | 7 | -
- | - | - | 39 | 8 | -
- | - | - | 40 | 8 | -
- | - | - | 41 | 8 | -
- | - | - | 42 | 8 | -
- | - | - | 43 | 8 | -
- | - | - | 44 | 9 | -
- | - | - | 45 | 9 | -
- | - | - | 46 | 9 | -
- | - | - | 47 | 9 | -
- | - | - | 48 | 9 | -
- | - | - | 49 | 9 | -
- | - | - | 50 | 10 | -
- | - | - | 51 | 10 | -
- | - | - | 52 | 10 | -
- | - | - | 53 | 10 | -
- | - | - | 54 | 10 | -
- | - | - | 55 | 11 | -
- | - | - | 56 | 11 | -
- | - | - | 57 | 11 | -
- | - | - | 58 | 11 | -
- | - | - | 59 | 11 | -
- | - | - | 60 | 11 | -
- | - | - | 61 | 12 | -
- | - | - | 62 | 12 | -
- | - | - | 63 | 12 | -
- | - | - | 64 | 12 | -
- | - | - | 65 | 12 | -
- | - | - | 66 | 13 | -
- | - | - | 67 | 13 | -
- | - | - | 68 | 13 | -
- | - | - | 69 | #REF! | #REF!
- | - | - | 70 | #REF! | #REF!
- | - | - | 71 | #REF! | #REF!
- | - | - | 72 | #REF! | #REF!
- | - | - | 73 | #REF! | #REF!
- | - | - | 74 | #REF! | #REF!
- | - | - | 75 | #REF! | #REF!
- | - | - | 76 | #REF! | #REF!
- | - | - | 77 | #REF! | #REF!
- | - | - | 78 | #REF! | #REF!
- | - | - | 79 | #REF! | #REF!
- | - | - | 80 | #REF! | #REF!
- | - | - | 81 | #REF! | #REF!
- | - | - | 82 | #REF! | #REF!
- | - | - | 83 | #REF! | #REF!
- | - | - | 84 | #REF! | #REF!
- | - | - | 85 | #REF! | #REF!
- | - | - | 86 | #REF! | #REF!
- | - | - | 87 | #REF! | #REF!
- | - | - | 88 | #REF! | #REF!
- | - | - | 89 | #REF! | #REF!
- | - | - | 90 | #REF! | #REF!
- | - | - | 91 | #REF! | #REF!
- | - | - | 92 | #REF! | #REF!
- | - | - | 93 | #REF! | #REF!
- | - | - | 94 | #REF! | #REF!
- | - | - | 95 | #REF! | #REF!
- | - | - | 96 | #REF! | #REF!
- | - | - | 97 | #REF! | #REF!
- | - | - | 98 | #REF! | #REF!
- | - | - | 99 | #REF! | #REF!
Next Week
Activity | Status | Date | Nr | Period | Project
Document the High Level Human Centred Design Themes and Principles. | In Progress | 2020-06-01 | 0 | 3 | Student Experience - Credit Management
As-Is Mini planning sessin (Domestic HE to HE, Project Manager) | Not Started | 2020-06-01 | 1 | 3 | Student Experience - Credit Management
High Level Human Centred Design Themes and Principles. | In Progress | 2020-06-01 | 2 | 3 | Student Experience - Credit Management
Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | 2020-06-02 | 3 | 3 | Student Experience - Credit Management
Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | 2020-06-03 | 4 | 3 | Student Experience - Credit Management
Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | 2020-06-04 | 5 | 3 | Student Experience - Credit Management
Targeted feedback, 1-on-1 sessions and updates of CJMs and As-Is business processes | Not Started | 2020-06-05 | 6 | 3 | Student Experience - Credit Management
- | - | - | 7 | 4 | -
- | - | - | 8 | 4 | -
- | - | - | 9 | 4 | -
- | - | - | 10 | 4 | -
- | - | - | 11 | 4 | -
- | - | - | 12 | 4 | -
- | - | - | 13 | 4 | -
- | - | - | 14 | 5 | -
- | - | - | 15 | 5 | -
- | - | - | 16 | 5 | -
- | - | - | 17 | 5 | -
- | - | - | 18 | 5 | -
- | - | - | 19 | 6 | -
- | - | - | 20 | 6 | -
- | - | - | 21 | 6 | -
- | - | - | 22 | 6 | -
- | - | - | 23 | 6 | -
- | - | - | 24 | 6 | -
- | - | - | 25 | 7 | -
- | - | - | 26 | 7 | -
- | - | - | 27 | 7 | -
- | - | - | 28 | 7 | -
- | - | - | 29 | 7 | -
- | - | - | 30 | 8 | -
- | - | - | 31 | 8 | -
- | - | - | 32 | 8 | -
- | - | - | 33 | 8 | -
- | - | - | 34 | 8 | -
- | - | - | 35 | 9 | -
- | - | - | 36 | 9 | -
- | - | - | 37 | 9 | -
- | - | - | 38 | 9 | -
- | - | - | 39 | 9 | -
- | - | - | 40 | 9 | -
- | - | - | 41 | 10 | -
- | - | - | 42 | 10 | -
- | - | - | 43 | 10 | -
- | - | - | 44 | 10 | -
- | - | - | 45 | 10 | -
- | - | - | 46 | 11 | -
- | - | - | 47 | 11 | -
- | - | - | 48 | 11 | -
- | - | - | 49 | 11 | -
- | - | - | 50 | 11 | -
- | - | - | 51 | 11 | -
- | - | - | 52 | 12 | -
- | - | - | 53 | 12 | -
- | - | - | 54 | 12 | -
- | - | - | 55 | 12 | -
- | - | - | 56 | 12 | -
- | - | - | 57 | 13 | -
- | - | - | 58 | 13 | -
- | - | - | 59 | 13 | -
- | - | - | 60 | #REF! | #REF!
- | - | - | 61 | #REF! | #REF!
- | - | - | 62 | #REF! | #REF!
- | - | - | 63 | #REF! | #REF!
- | - | - | 64 | #REF! | #REF!
- | - | - | 65 | #REF! | #REF!
- | - | - | 66 | #REF! | #REF!
- | - | - | 67 | #REF! | #REF!
- | - | - | 68 | #REF! | #REF!
- | - | - | 69 | #REF! | #REF!
- | - | - | 70 | #REF! | #REF!
- | - | - | 71 | #REF! | #REF!
- | - | - | 72 | #REF! | #REF!
- | - | - | 73 | #REF! | #REF!
- | - | - | 74 | #REF! | #REF!
- | - | - | 75 | #REF! | #REF!
- | - | - | 76 | #REF! | #REF!
- | - | - | 77 | #REF! | #REF!
- | - | - | 78 | #REF! | #REF!
- | - | - | 79 | #REF! | #REF!
- | - | - | 80 | #REF! | #REF!
- | - | - | 81 | #REF! | #REF!
- | - | - | 82 | #REF! | #REF!
- | - | - | 83 | #REF! | #REF!
- | - | - | 84 | #REF! | #REF!
- | - | - | 85 | #REF! | #REF!
- | - | - | 86 | #REF! | #REF!
- | - | - | 87 | #REF! | #REF!
- | - | - | 88 | #REF! | #REF!
- | - | - | 89 | #REF! | #REF!
- | - | - | 90 | #REF! | #REF!
- | - | - | 91 | #REF! | #REF!
- | - | - | 92 | #REF! | #REF!
- | - | - | 93 | #REF! | #REF!
- | - | - | 94 | #REF! | #REF!
- | - | - | 95 | #REF! | #REF!
- | - | - | 96 | #REF! | #REF!
- | - | - | 97 | #REF! | #REF!
- | - | - | 98 | #REF! | #REF!
- | - | - | 99 | #REF! | #REF!
Issues Raised This Week
Description | Impact | Potential Solution | Nr | Period | Project | Status
- | - | - | 0 | 2 | Student Experience - Credit Management | Resolved
- | - | - | 1 | -6282 | - | -
- | - | - | 2 | #REF! | #REF! | #REF!
- | - | - | 3 | #REF! | #REF! | #REF!
- | - | - | 4 | #REF! | #REF! | #REF!
- | - | - | 5 | #REF! | #REF! | #REF!
Risks Raised This Week
Description | Impact | Potential Mitigation | Nr | Period | Project | Status
Current focus is mainly on the Blue Sky thinking angle of the project. Week starting 1 June 2020 BAPL will be focusing on the As-Is business processes so that an anchor for the gap analysis is established. | Medium | BAPL has already started analysis work on the As-Is business processes. BAPL has also scheduled a process workshop kick-off with Domestic HE to HE for Monday 1 June 2020 | 0 | 2 | Student Experience - Credit Management | Open
- | - | - | 1 | -6282 | - | -
- | - | - | 2 | -6282 | - | -
- | - | - | 3 | -6282 | - | -
- | - | - | 4 | #REF! | #REF! | #REF!
- | - | - | 5 | #REF! | #REF! | #REF!
Formulas:
Start Date = IF(ISERROR(VLOOKUP(A10,T_ProjectList[],3)),"-",VLOOKUP(A10,T_ProjectList[],3))
End date = IF(ISERROR(VLOOKUP(A10,T_ProjectList[],4)),"-",VLOOKUP(A10,T_ProjectList[],4))
End date = IF(ISERROR(INDEX(T_Activities[],E12+[First Row of Current Period Issues],2)),"-",IF(AND([First Row Current Period Risks]=B13,[Project]=A10),INDEX(T_Activities[],E12+[First Row of Current Period Issues],2),"-"))
Note on B1: 5 STATUS REPORT, SINGLE PROJECT Only use either '5 Status Report, Single Project' OR '6 Status Report, Group Projects'. Use this status report if you wish to produce ONE status report PER PROJECT as opposed to multiple projects grouped by your own status group assigned in '1 Controls'.
Note on C7: Lead BA Please select he lead BA for this project.
Note on A10: SELECT PROJECT Select project for which you would like to report the status.
Note on B12: STATUS REPORT WEEK Please enter the end date of the week you would like to report.
Note on B14: PROJECT STATUS Choose the project status based on the following guidelines: ‘Green’: Initiative is on track in terms of time, cost and quality of analysis work. No identified issues or risks are likely to impact initiative health ‘Orange’: Identified issues or risks have potential to impact time, cost or quality of analysis work, however an effective mitigation strategy is in place for each ‘Red’: Either: Identified issues or risks are likely to impact time, cost or quality of analysis work and no effective mitigation strategy is in place to remediate; OR Identified issues or materialised risks are actually impacting time, cost or quality of analysis work.
Note on A18: APPLY FILTER After choosing the project and entering the relevant date you have to apply the filter to remove empty rows. Click on the little arrow next to the activity column and unselect '-'. You only have to do this for 1 column per table. *IMPORTANT* Once you change the date or select a different project, you have to reapply the filter for each table. Click on the filter icon, click 'Select all' and then untick '-' again.

## Settings (hidden)
Date | Holiday | State | Is Holiday | Valid Dates | Day | Dates retrieved from: | state dropdown values | activity status dropdown | % complete dropdown values | risk status dropdown | project status | project status meanings |  | engagement effort types | constraint | project timeline | impact
2016-01-01 | New Year's Day | National | TRUE | 2016-01-01 | 2016-01-01 | http://publicholidays.com.au | TAS | In Progress | 0% | Open | Green | Green | Initiative is on track in terms of time, cost and quality of analysis work. No identified issues or risks are likely to impact initiative health. | Effort consumption | Hard constraint | Fixed end date | Trivial
2016-01-06 | Devonport Cup ^ | TAS | FALSE | 01/01/1900 | 0 |  | WA | Completed | 10% | Resolved | Orange | Orange | Identified issues or risks have potential to impact time, cost or quality of analysis work, however an effective mitigation strategy is in place for each. | Effort increase | Estimated | Flexible end date | Low
2016-01-26 | Australia Day | National | TRUE | 2016-01-26 | 2016-01-26 |  | ACT | Not Started | 20% |  | Red | Red | Identified issues or risks are likely to impact time, cost or quality of analysis work and no effective mitigation strategy is in place to remediate; OR Identified issues or materialised risks are actually impacting time, cost or quality of analysis work. | Leave |  |  | Medium
2016-02-08 | Royal Hobart Regatta ^ | TAS | FALSE | 01/01/1900 | 2016-02-08 |  | SA | Rescheduled | 30% | [7 empty] | High
2016-02-24 | Launceston Cup ^ | TAS | FALSE | 01/01/1900 | 2016-02-24 |  | VIC | Cancelled | 40% | [7 empty] | Blocker
2016-03-07 | Labour Day | WA | FALSE | 01/01/1900 | 2016-03-07 |  | QLD |  | 50%
2016-03-01 | King Island Show ^ | TAS | FALSE | 01/01/1900 | 2016-03-01 |  | NT |  | 60%
2016-03-14 | Canberra Day | ACT, SA, TAS, VIC | FALSE | 01/01/1900 | 2016-03-14 |  | NSW |  | 70%
2016-03-25 | Good Friday | National | TRUE | 2016-03-25 | 2016-03-25 |  |  |  | 80%
2016-03-26 | Easter Saturday | National | TRUE | 01/01/1900 | 2016-03-26 |  |  |  | 90%
2016-03-27 | Easter Sunday | ACT, NSW & VIC | FALSE | 01/01/1900 | 2016-03-27 |  |  |  | 100%
2016-03-28 | Easter Monday | National | TRUE | 2016-03-28 | 2016-03-28
2016-03-29 | Anzac Day | National | TRUE | 2016-03-29 | 2016-03-29
2016-05-02 | Labour Day*** | QLD, NT | TRUE | 2016-05-02 | 2016-05-02
2016-05-06 | AGFEST ^ | TAS | FALSE | 01/01/1900 | 2016-05-06
2016-06-06 | Western Australia Day | WA | FALSE | 01/01/1900 | 2016-06-06
2016-06-13 | Queen's Birthday | National | TRUE | 2016-06-13 | 2016-06-13
2016-06-24 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2016-06-24
2016-07-01 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2016-07-01
2016-07-08 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2016-07-08
2016-07-15 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2016-07-15
2016-07-22 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2016-07-22
2016-08-01 | Picnic Day | NT | FALSE | 01/01/1900 | 2016-08-01
2016-08-10 | Royal Queensland Show ^ | QLD | TRUE | 2016-08-10 | 2016-08-10
2016-09-26 | Family and Community Day | ACT, WA | FALSE | 01/01/1900 | 2016-09-26
2016-09-30 | Burnie Show ^ | TAS, VIC | FALSE | 01/01/1900 | 2016-09-30
2016-10-03 | Queen's Birthday*** | QLD, ACT, NSW & SA | TRUE | 2016-10-03 | 2016-10-03
2016-10-06 | Royal Launceston Show ^ | TAS | FALSE | 01/01/1900 | 2016-10-06
2016-10-14 | Flinders Island Show ^ | TAS | FALSE | 01/01/1900 | 2016-10-14
2016-10-20 | Royal Hobart Show ^ | TAS | FALSE | 01/01/1900 | 2016-10-20
2016-11-01 | Melbourne Cup Day ** | VIC | FALSE | 01/01/1900 | 2016-11-01
2016-11-07 | Recreation Day ^ | TAS | FALSE | 01/01/1900 | 2016-11-07
2016-11-25 | Devonport Show ^ | TAS | FALSE | 01/01/1900 | 2016-11-25
2016-12-24 | Christmas Eve * | SA | FALSE | 01/01/1900 | 2016-12-24
2016-12-25 | Christmas Day | National | TRUE | 01/01/1900 | 2016-12-25
2016-12-26 | Boxing Day | National | TRUE | 2016-12-26 | 2016-12-26
2016-12-27 | Christmas Holidays | National | TRUE | 2016-12-27 | 2016-12-27
2016-12-31 | New Year's Eve * | SA | FALSE | 01/01/1900 | 2016-12-31
2017-01-01 | New Year's Day | National | TRUE | 01/01/1900 | 2017-01-01
2017-01-02 | New Year's Day | National | TRUE | 2017-01-02 | 2017-01-02
2017-01-11 | Devonport Cup ^ | TAS | FALSE | 01/01/1900 | 2017-01-11
2017-01-26 | Australia Day | National | TRUE | 2017-01-26 | 2017-01-26
2017-02-13 | Royal Hobart Regatta ^ | TAS | FALSE | 01/01/1900 | 2017-02-13
2017-02-22 | Launceston Cup ^ | TAS | FALSE | 01/01/1900 | 2017-02-22
2017-03-06 | Labour Day | WA | FALSE | 01/01/1900 | 2017-03-06
2017-03-07 | King Island Show ^ | TAS | FALSE | 01/01/1900 | 2017-03-07
2017-03-13 | Canberra Day | ACT, SA, TAS, VIC | FALSE | 01/01/1900 | 2017-03-13
2017-04-14 | Good Friday | National | TRUE | 2017-04-14 | 2017-04-14
2017-04-15 | Easter Saturday | National | TRUE | 01/01/1900 | 2017-04-15
2017-04-16 | Easter Sunday | ACT, NSW & VIC | FALSE | 01/01/1900 | 2017-04-16
2017-04-17 | Easter Monday | National | TRUE | 2017-04-17 | 2017-04-17
2017-04-18 | Easter Tuesday ^^ | TAS | FALSE | 01/01/1900 | 2017-04-18
2017-04-25 | Anzac Day | National | TRUE | 2017-04-25 | 2017-04-25
2017-05-05 | AGFEST ^ | TAS | FALSE | 01/01/1900 | 2017-05-05
2017-05-01 | May Day | NT, QLD | TRUE | 2017-05-01 | 2017-05-01
2017-06-05 | Western Australia Day | WA | FALSE | 01/01/1900 | 2017-06-05
2017-06-12 | Queen's Birthday | National | TRUE | 2017-06-12 | 2017-06-12
2017-06-30 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2017-06-30
2017-07-07 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2017-07-07
2017-07-14 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2017-07-14
2017-07-21 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2017-07-21
2017-07-28 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2017-07-28
2017-08-07 | Picnic Day | NT | FALSE | 01/01/1900 | 2017-08-07
2017-08-16 | Royal Queensland Show ^ | QLD | TRUE | 2017-08-16 | 2017-08-16
2017-09-25 | Family and Community Day | ACT, WA | FALSE | 01/01/1900 | 2017-09-25
2017-10-06 | Burnie Show ^ | TAS | FALSE | 01/01/1900 | 2017-10-06
2017-10-02 | Labour Day | ACT, NSW & SA, QLD | TRUE | 2017-10-02 | 2017-10-02
2017-10-12 | Royal Launceston Show ^ | TAS | FALSE | 01/01/1900 | 2017-10-12
2017-10-20 | Flinders Island Show ^ | TAS | FALSE | 01/01/1900 | 2017-10-20
2017-10-26 | Royal Hobart Show ^ | TAS | FALSE | 01/01/1900 | 2017-10-26
2017-11-06 | Recreation Day ^ | TAS | FALSE | 01/01/1900 | 2017-11-06
2017-11-07 | Melbourne Cup Day ** | VIC | FALSE | 01/01/1900 | 2017-11-07
2017-12-01 | Devonport Show ^ | TAS | FALSE | 01/01/1900 | 2017-12-01
2017-12-24 | Christmas Eve * | SA | FALSE | 01/01/1900 | 2017-12-24
2017-12-25 | Christmas Day | National | TRUE | 2017-12-25 | 2017-12-25
2017-12-26 | Boxing Day | National | TRUE | 2017-12-26 | 2017-12-26
2017-12-26 | Proclamation Day | SA | FALSE | 01/01/1900 | 2017-12-26
2017-12-31 | New Year's Eve * | SA | FALSE | 01/01/1900 | 2017-12-31
2018-01-01 | New Year's Day | National | TRUE | 2018-01-01 | 2018-01-01
2018-01-10 | Devonport Cup | TAS | FALSE | 01/01/1900 | 2018-01-10
2018-01-26 | Australia Day | National | TRUE | 2018-01-26 | 2018-01-26
2018-02-12 | Royal Hobart Regatta | TAS | FALSE | 01/01/1900 | 2018-02-12
2018-02-28 | Launceston Cup | TAS | FALSE | 01/01/1900 | 2018-02-28
2018-03-05 | Labour Day | WA | FALSE | 01/01/1900 | 2018-03-05
2018-03-06 | King Island Show | TAS | FALSE | 01/01/1900 | 2018-03-06
2018-03-12 | Canberra Day | ACT | FALSE | 01/01/1900 | 2018-03-12
2018-03-12 | March Public Holiday | SA | FALSE | 01/01/1900 | 2018-03-12
2018-03-12 | Eight Hours Day | TAS | FALSE | 01/01/1900 | 2018-03-12
2018-03-12 | Labour Day | VIC | FALSE | 01/01/1900 | 2018-03-12
2018-03-30 | Good Friday | National | TRUE | 2018-03-30 | 2018-03-30
2018-03-31 | Day following Good Friday | National except TAS & WA | FALSE | 01/01/1900 | 2018-03-31 |  | QLD, NSW, VIC, NT, SA, QA, TAS
2018-04-01 | Easter Sunday | ACT, NSW, QLD & VIC | TRUE | 01/01/1900 | 2018-04-01
2018-04-02 | Easter Monday | National | TRUE | 2018-04-02 | 2018-04-02
2018-04-03 | Easter Tuesday * | TAS | FALSE | 01/01/1900 | 2018-04-03
2018-04-25 | Anzac Day | National | TRUE | 2018-04-25 | 2018-04-25
2018-05-04 | AGFEST | TAS | FALSE | 01/01/1900 | 2018-05-04
2018-05-07 | May Day | NT | FALSE | 01/01/1900 | 2018-05-07
2018-05-07 | Labour Day | QLD | TRUE | 2018-05-07 | 2018-05-07
2018-05-28 | Reconciliation Day | ACT | FALSE | 01/01/1900 | 2018-05-28
2018-06-04 | Western Australia Day | WA | FALSE | 01/01/1900 | 2018-06-04
2018-06-11 | Queen's Birthday | National except QLD & WA | TRUE | 2018-06-11 | 2018-06-11
2018-06-29 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2018-06-29
2018-07-06 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2018-07-06
2018-07-13 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2018-07-13
2018-07-20 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2018-07-20
2018-07-27 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2018-07-27
2018-08-06 | Picnic Day | NT | FALSE | 01/01/1900 | 2018-08-06
2018-08-15 | Ekka Wednesday * | QLD | TRUE | 2018-08-15 | 2018-08-15
2018-09-24 | Queen's Birthday | WA | FALSE | 01/01/1900 | 2018-09-24
2018-09-28 | AFL Grand Final Friday | VIC | FALSE | 01/01/1900 | 2018-09-28
2018-10-01 | Labour Day | ACT, NSW & SA | FALSE | 01/01/1900 | 2018-10-01
2018-10-01 | Queen's Birthday | QLD | TRUE | 2018-10-01 | 2018-10-01
2018-10-05 | Burnie Show | TAS | FALSE | 01/01/1900 | 2018-10-05
2018-10-11 | Royal Launceston Show | TAS | FALSE | 01/01/1900 | 2018-10-11
2018-10-19 | Flinders Island Show | TAS | FALSE | 01/01/1900 | 2018-10-19
2018-10-25 | Royal Hobart Show | TAS | FALSE | 01/01/1900 | 2018-10-25
2018-11-05 | Recreation Day | TAS | FALSE | 01/01/1900 | 2018-11-05
2018-11-06 | Melbourne Cup Day * | VIC | FALSE | 01/01/1900 | 2018-11-06
2018-11-30 | Devonport Show | TAS | FALSE | 01/01/1900 | 2018-11-30
2018-12-24 | Christmas Eve * | SA | FALSE | 01/01/1900 | 2018-12-24
2018-12-25 | Christmas Day | National | TRUE | 2018-12-25 | 2018-12-25
2018-12-26 | Boxing Day | National except SA | FALSE | 01/01/1900 | 2018-12-26
2018-12-26 | Proclamation Day | SA | FALSE | 01/01/1900 | 2018-12-26
2018-12-31 | New Year's Eve * | SA | FALSE | 01/01/1900 | 2018-12-31
2019-01-01 | New Year's Day | National | TRUE | 2019-01-01 | 2019-01-01
2019-01-09 | Devonport Cup | TAS | FALSE | 01/01/1900 | 2019-01-09
2019-01-28 | Australia Day Holiday | National | TRUE | 2019-01-28 | 2019-01-28
2019-02-11 | Royal Hobart Regatta | TAS | FALSE | 01/01/1900 | 2019-02-11
2019-02-27 | Launceston Cup | TAS | FALSE | 01/01/1900 | 2019-02-27
2019-03-04 | Labour Day | WA | FALSE | 01/01/1900 | 2019-03-04
2019-03-05 | King Island Show | TAS | FALSE | 01/01/1900 | 2019-03-05
2019-03-11 | Canberra Day | ACT | FALSE | 01/01/1900 | 2019-03-11
2019-03-11 | March Public Holiday | SA | FALSE | 01/01/1900 | 2019-03-11
2019-03-11 | Eight Hours Day | TAS | FALSE | 01/01/1900 | 2019-03-11
2019-03-11 | Labour Day | VIC | FALSE | 01/01/1900 | 2019-03-11
2019-04-19 | Good Friday | National | TRUE | 2019-04-19 | 2019-04-19
2019-04-20 | Day following Good Friday | National except TAS & WA | FALSE | 01/01/1900 | 2019-04-20
2019-04-21 | Easter Sunday | ACT, NSW, QLD & VIC | TRUE | 01/01/1900 | 2019-04-21
2019-04-22 | Easter Monday | National | TRUE | 2019-04-22 | 2019-04-22
2019-04-23 | Easter Tuesday * | TAS | FALSE | 01/01/1900 | 2019-04-23
2019-04-25 | Anzac Day | National | TRUE | 2019-04-25 | 2019-04-25
2019-05-03 | AGFEST | TAS | FALSE | 01/01/1900 | 2019-05-03
2019-05-06 | May Day | NT | FALSE | 01/01/1900 | 2019-05-06
2019-05-06 | Labour Day | QLD | TRUE | 2019-05-06 | 2019-05-06
2019-05-27 | Reconciliation Day | ACT | FALSE | 01/01/1900 | 2019-05-27
2019-06-03 | Western Australia Day | WA | FALSE | 01/01/1900 | 2019-06-03
2019-06-10 | Queen's Birthday | National except QLD & WA | TRUE | 2019-06-10 | 2019-06-10
2019-06-28 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2019-06-28
2019-07-05 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2019-07-05
2019-07-12 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2019-07-12
2019-07-19 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2019-07-19
2019-07-26 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2019-07-26
2019-08-05 | Picnic Day | NT | FALSE | 01/01/1900 | 2019-08-05
2019-08-14 | Ekka Wednesday * | QLD | TRUE | 2019-08-14 | 2019-08-14
2019-09-27 | AFL Grand Final Friday | VIC | FALSE | 01/01/1900 | 2019-09-27
2019-09-30 | Queen's Birthday | WA | FALSE | 01/01/1900 | 2019-09-30
2019-10-04 | Burnie Show | TAS | FALSE | 01/01/1900 | 2019-10-04
2019-10-07 | Labour Day | ACT, NSW & SA | FALSE | 01/01/1900 | 2019-10-07
2019-10-07 | Queen's Birthday | QLD | TRUE | 2019-10-07 | 2019-10-07
2019-10-10 | Royal Launceston Show | TAS | FALSE | 01/01/1900 | 2019-10-10
2019-10-18 | Flinders Island Show | TAS | FALSE | 01/01/1900 | 2019-10-18
2019-10-24 | Royal Hobart Show | TAS | FALSE | 01/01/1900 | 2019-10-24
2019-11-04 | Recreation Day | TAS | FALSE | 01/01/1900 | 2019-11-04
2019-11-05 | Melbourne Cup Day * | VIC | FALSE | 01/01/1900 | 2019-11-05
2019-11-29 | Devonport Show | TAS | FALSE | 01/01/1900 | 2019-11-29
2019-12-24 | Christmas Eve * | NT & SA | FALSE | 01/01/1900 | 2019-12-24
2019-12-25 | Christmas Day | National | TRUE | 2019-12-25 | 2019-12-25
2019-12-26 | Boxing Day | QLD, NSW, VIC, NT, QA, TAS | TRUE | 2019-12-26 | 2019-12-26
2019-12-26 | Proclamation Day | SA | FALSE | 01/01/1900 | 2019-12-26
2019-12-31 | New Year's Eve * | NT, SA | FALSE | 01/01/1900 | 2019-12-31
2020-01-01 | New Year's Day | National | TRUE | 2020-01-01 | 2020-01-01
2020-01-08 | Devonport Cup | TAS | FALSE | 01/01/1900 | 2020-01-08
2020-01-27 | Australia Day Holiday | National | TRUE | 2020-01-27 | 2020-01-27
2020-02-10 | Royal Hobart Regatta | TAS | FALSE | 01/01/1900 | 2020-02-10
2020-02-26 | Launceston Cup | TAS | FALSE | 01/01/1900 | 2020-02-26
2020-03-02 | Labour Day | WA | FALSE | 01/01/1900 | 2020-03-02
2020-03-03 | King Island Show | TAS | FALSE | 01/01/1900 | 2020-03-03
2020-03-09 | Canberra Day | ACT | FALSE | 01/01/1900 | 2020-03-09
2020-03-09 | March Public Holiday | SA | FALSE | 01/01/1900 | 2020-03-09
2020-03-09 | Eight Hours Day | TAS | FALSE | 01/01/1900 | 2020-03-09
2020-03-09 | Labour Day | VIC | FALSE | 01/01/1900 | 2020-03-09
2020-04-10 | Good Friday | National | TRUE | 2020-04-10 | 2020-04-10
2020-04-11 | Day following Good Friday | QLD, NSW, VIC, NT, SA | TRUE | 01/01/1900 | 2020-04-11
2020-04-12 | Easter Sunday | ACT, NSW, QLD & VIC | TRUE | 01/01/1900 | 2020-04-12
2020-04-13 | Easter Monday | National | TRUE | 2020-04-13 | 2020-04-13
2020-04-14 | Easter Tuesday * | TAS | FALSE | 01/01/1900 | 2020-04-14
2020-04-25 | Anzac Day | National | TRUE | 01/01/1900 | 2020-04-25
2020-04-27 | Anzac Day Holiday | WA | FALSE | 01/01/1900 | 2020-04-27
2020-05-04 | May Day | NT | FALSE | 01/01/1900 | 2020-05-04
2020-05-04 | Labour Day | QLD | TRUE | 2020-05-04 | 2020-05-04
2020-05-08 | AGFEST | TAS | FALSE | 01/01/1900 | 2020-05-08
2020-06-01 | Reconciliation Day | ACT | FALSE | 01/01/1900 | 2020-06-01
2020-06-01 | Western Australia Day | WA | FALSE | 01/01/1900 | 2020-06-01
2020-06-08 | Queen's Birthday | NSW, VIC, NT, SA, TAS | FALSE | 01/01/1900 | 2020-06-08
2020-06-26 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2020-06-26
2020-07-03 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2020-07-03
2020-07-10 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2020-07-10
2020-07-17 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2020-07-17
2020-07-24 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2020-07-24
2020-08-03 | Picnic Day | NT | FALSE | 01/01/1900 | 2020-08-03
2020-08-12 | Ekka Wednesday * | QLD | TRUE | 2020-08-12 | 2020-08-12
#VALUE! | AFL Grand Final Friday | VIC | FALSE | #VALUE! | #VALUE!
2020-09-28 | Queen's Birthday | WA | FALSE | 01/01/1900 | 2020-09-28
2020-10-02 | Burnie Show | TAS | FALSE | 01/01/1900 | 2020-10-02
2020-10-05 | Labour Day | ACT, NSW & SA | FALSE | 01/01/1900 | 2020-10-05
2020-10-05 | Queen's Birthday | QLD | TRUE | 2020-10-05 | 2020-10-05
2020-10-08 | Royal Launceston Show | TAS | FALSE | 01/01/1900 | 2020-10-08
2020-10-16 | Flinders Island Show | TAS | FALSE | 01/01/1900 | 2020-10-16
2020-10-22 | Royal Hobart Show | TAS | FALSE | 01/01/1900 | 2020-10-22
2020-11-02 | Recreation Day | TAS | FALSE | 01/01/1900 | 2020-11-02
2020-11-03 | Melbourne Cup Day * | VIC | FALSE | 01/01/1900 | 2020-11-03
2020-11-27 | Devonport Show | TAS | FALSE | 01/01/1900 | 2020-11-27
2020-12-24 | Christmas Eve * | NT & SA | FALSE | 01/01/1900 | 2020-12-24
2020-12-25 | Christmas Day | National | TRUE | 2020-12-25 | 2020-12-25
2020-12-26 | Boxing Day | QLD, NSW, VIC, NT, WA, TAS | TRUE | 01/01/1900 | 2020-12-26
2020-12-26 | Proclamation Day | SA | FALSE | 01/01/1900 | 2020-12-26
2020-12-28 | Proclamation Day Holiday | SA | FALSE | 01/01/1900 | 2020-12-28
2020-12-28 | Boxing Day Holiday | QLD, NSW, VIC, NT, WA, TAS | TRUE | 2020-12-28 | 2020-12-28
2020-12-31 | New Year's Eve * | NT & SA | FALSE | 01/01/1900 | 2020-12-31
2021-01-01 | New Year's Day | National | TRUE | 2021-01-01 | 2021-01-01
2021-01-06 | Devonport Cup | TAS | FALSE | 01/01/1900 | 2021-01-06
2021-01-26 | Australia Day | National | TRUE | 2021-01-26 | 2021-01-26
2021-02-08 | Royal Hobart Regatta | TAS | FALSE | 01/01/1900 | 2021-02-08
2021-02-24 | Launceston Cup | TAS | FALSE | 01/01/1900 | 2021-02-24
2021-03-01 | Labour Day | WA | FALSE | 01/01/1900 | 2021-03-01
2021-03-02 | King Island Show | TAS | FALSE | 01/01/1900 | 2021-03-02
2021-03-08 | March Public Holiday | SA | FALSE | 01/01/1900 | 2021-03-08
2021-03-08 | Canberra Day | ACT | FALSE | 01/01/1900 | 2021-03-08
2021-03-08 | Eight Hours Day | TAS | FALSE | 01/01/1900 | 2021-03-08
2021-03-08 | Labour Day | VIC | FALSE | 01/01/1900 | 2021-03-08
2021-04-02 | Good Friday | National | TRUE | 2021-04-02 | 2021-04-02
2021-04-03 | Day following Good Friday | QLD, NSW, VIC, NT, SA | TRUE | 01/01/1900 | 2021-04-03
2021-04-04 | Easter Sunday | ACT, NSW, QLD & VIC | TRUE | 01/01/1900 | 2021-04-04
2021-04-05 | Easter Monday | National | TRUE | 2021-04-05 | 2021-04-05
2021-04-06 | Easter Tuesday * | TAS | FALSE | 01/01/1900 | 2021-04-06
2021-04-25 | Anzac Day | National | TRUE | 01/01/1900 | 2021-04-25
2021-04-26 | Anzac Day Holiday | ACT, SA & WA | FALSE | 01/01/1900 | 2021-04-26
2021-05-03 | Labour Day | QLD | TRUE | 2021-05-03 | 2021-05-03
2021-05-03 | May Day | NT | FALSE | 01/01/1900 | 2021-05-03
2021-05-07 | AGFEST | TAS | FALSE | 01/01/1900 | 2021-05-07
2021-05-31 | Reconciliation Day | ACT | FALSE | 01/01/1900 | 2021-05-31
2021-06-07 | Western Australia Day | WA | FALSE | 01/01/1900 | 2021-06-07
2021-06-14 | Queen's Birthday | NSW, VIC, NT, SA, TAS | FALSE | 01/01/1900 | 2021-06-14
2021-06-25 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2021-06-25
2021-07-02 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2021-07-02
2021-07-09 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2021-07-09
2021-07-16 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2021-07-16
2021-07-23 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2021-07-23
2021-08-02 | Picnic Day | NT | FALSE | 01/01/1900 | 2021-08-02
2021-08-11 | Ekka Wednesday * | QLD | TRUE | 2021-08-11 | 2021-08-11
#VALUE! | AFL Grand Final Friday | VIC | FALSE | #VALUE! | #VALUE!
2021-09-27 | Queen's Birthday | WA | FALSE | 01/01/1900 | 2021-09-27
2021-10-01 | Burnie Show | TAS | FALSE | 01/01/1900 | 2021-10-01
2021-10-04 | Labour Day | ACT, NSW & SA | FALSE | 01/01/1900 | 2021-10-04
2021-10-04 | Queen's Birthday | QLD | TRUE | 2021-10-04 | 2021-10-04
2021-10-07 | Royal Launceston Show | TAS | FALSE | 01/01/1900 | 2021-10-07
2021-10-15 | Flinders Island Show | TAS | FALSE | 01/01/1900 | 2021-10-15
2021-10-21 | Royal Hobart Show | TAS | FALSE | 01/01/1900 | 2021-10-21
2021-11-01 | Recreation Day | TAS | FALSE | 01/01/1900 | 2021-11-01
2021-11-02 | Melbourne Cup Day * | VIC | FALSE | 01/01/1900 | 2021-11-02
2021-11-26 | Devonport Show | TAS | FALSE | 01/01/1900 | 2021-11-26
2021-12-24 | Christmas Eve * | NT & SA | FALSE | 01/01/1900 | 2021-12-24
2021-12-25 | Christmas Day | National | TRUE | 01/01/1900 | 2021-12-25
2021-12-26 | Boxing Day | QLD, NSW, VIC, NT, WA, TAS | TRUE | 01/01/1900 | 2021-12-26
2021-12-26 | Proclamation Day | SA | FALSE | 01/01/1900 | 2021-12-26
2021-12-27 | Christmas Holiday | National | TRUE | 2021-12-27 | 2021-12-27
2021-12-28 | Boxing Day Holiday | QLD, NSW, VIC, NT, WA, TAS | TRUE | 2021-12-28 | 2021-12-28
2021-12-28 | Proclamation Day Holiday | SA | FALSE | 01/01/1900 | 2021-12-28
2021-12-31 | New Year's Eve * | NT & SA | FALSE | 01/01/1900 | 2021-12-31
2022-01-01 | New Year's Day | National | TRUE | 01/01/1900 | 2022-01-01
2022-01-03 | New Year Holiday | National | TRUE | 2022-01-03 | 2022-01-03
2022-01-05 | Devonport Cup | TAS | FALSE | 01/01/1900 | 2022-01-05
2022-01-26 | Australia Day | National | TRUE | 2022-01-26 | 2022-01-26
2022-02-14 | Royal Hobart Regatta | TAS | FALSE | 01/01/1900 | 2022-02-14
2022-02-23 | Launceston Cup | TAS | FALSE | 01/01/1900 | 2022-02-23
2022-03-01 | King Island Show | TAS | FALSE | 01/01/1900 | 2022-03-01
2022-03-07 | Labour Day | WA | FALSE | 01/01/1900 | 2022-03-07
2022-03-14 | March Public Holiday | SA | FALSE | 01/01/1900 | 2022-03-14
2022-03-14 | Canberra Day | ACT | FALSE | 01/01/1900 | 2022-03-14
2022-03-14 | Eight Hours Day | TAS | FALSE | 01/01/1900 | 2022-03-14
2022-03-14 | Labour Day | VIC | FALSE | 01/01/1900 | 2022-03-14
2022-04-15 | Good Friday | National | TRUE | 2022-04-15 | 2022-04-15
2022-04-16 | Day following Good Friday | QLD, NSW, VIC, NT, SA | TRUE | 01/01/1900 | 2022-04-16
2022-04-17 | Easter Sunday | ACT, NSW, QLD & VIC | TRUE | 01/01/1900 | 2022-04-17
2022-04-18 | Easter Monday | National | TRUE | 2022-04-18 | 2022-04-18
2022-04-19 | Easter Tuesday * | TAS | FALSE | 01/01/1900 | 2022-04-19
2022-04-25 | Anzac Day | National | TRUE | 2022-04-25 | 2022-04-25
2022-05-02 | Labour Day | QLD | TRUE | 2022-05-02 | 2022-05-02
2022-05-02 | May Day | NT | FALSE | 01/01/1900 | 2022-05-02
2022-05-06 | AGFEST | TAS | FALSE | 01/01/1900 | 2022-05-06
2022-05-30 | Reconciliation Day | ACT | FALSE | 01/01/1900 | 2022-05-30
2022-06-06 | Western Australia Day | WA | FALSE | 01/01/1900 | 2022-06-06
2022-06-13 | Queen's Birthday | NSW, VIC, NT, SA, TAS | FALSE | 01/01/1900 | 2022-06-13
2022-06-24 | Borroloola Show Day | NT | FALSE | 01/01/1900 | 2022-06-24
2022-07-01 | Alice Springs Show Day | NT | FALSE | 01/01/1900 | 2022-07-01
2022-07-08 | Tennant Creek Show Day | NT | FALSE | 01/01/1900 | 2022-07-08
2022-07-15 | Katherine Show Day | NT | FALSE | 01/01/1900 | 2022-07-15
2022-07-22 | Darwin Show Day | NT | FALSE | 01/01/1900 | 2022-07-22
2022-08-01 | Picnic Day | NT | FALSE | 01/01/1900 | 2022-08-01
2022-08-10 | Ekka Wednesday * | QLD | TRUE | 2022-08-10 | 2022-08-10
#VALUE! | AFL Grand Final Friday | VIC | FALSE | #VALUE! | #VALUE!
2022-09-26 | Queen's Birthday | WA | FALSE | 01/01/1900 | 2022-09-26
2022-09-30 | Burnie Show | TAS | FALSE | 01/01/1900 | 2022-09-30
2022-10-03 | Labour Day | ACT, NSW & SA | FALSE | 01/01/1900 | 2022-10-03
2022-10-03 | Queen's Birthday | QLD | TRUE | 2022-10-03 | 2022-10-03
2022-10-06 | Royal Launceston Show | TAS | FALSE | 01/01/1900 | 2022-10-06
2022-10-14 | Flinders Island Show | TAS | FALSE | 01/01/1900 | 2022-10-14
2022-10-20 | Royal Hobart Show | TAS | FALSE | 01/01/1900 | 2022-10-20
2022-11-01 | Melbourne Cup Day * | VIC | FALSE | 01/01/1900 | 2022-11-01
2022-11-07 | Recreation Day | TAS | FALSE | 01/01/1900 | 2022-11-07
2022-11-25 | Devonport Show | TAS | FALSE | 01/01/1900 | 2022-11-25
2022-12-24 | Christmas Eve * | NT & SA | FALSE | 01/01/1900 | 2022-12-24
2022-12-25 | Christmas Day | National | TRUE | 01/01/1900 | 2022-12-25
2022-12-26 | Boxing Day | QLD, NSW, VIC, NT, WA, TAS | TRUE | 2022-12-26 | 2022-12-26
2022-12-26 | Proclamation Day | SA | FALSE | 01/01/1900 | 2022-12-26
2022-12-27 | Christmas Holiday | National | TRUE | 2022-12-27 | 2022-12-27
2022-12-31 | New Year's Eve * | NT & SA | FALSE | 01/01/1900 | 2022-12-31
Formulas:
Valid Dates = IF(AND(Holidays[[#This Row],[Is Holiday]]=TRUE,WEEKDAY(Holidays[[#This Row],[Date]],2)<>7,WEEKDAY(Holidays[[#This Row],[Date]],2)<>6),Holidays[[#This Row],[Date]],"01/01/1900")
Day = Holidays[[#This Row],[Date]]